SORATHEL

Development Plan & Project Roadmap

FROM WORLD BIBLE TO PUBLISHED SERIAL

— ✦ —

Project Management Document — v1.0

February 2026

CONFIDENTIAL

# I. Project Overview

Sorathel is a fantasy serial that will be published episodically — like an HBO series — building an audience and community before expanding into manhwa and eventually a MOBA-style game. The story follows Vaelen, a successful and hollow practitioner at the center of a dying world, through a three-movement arc across three seasons.

Release Model

The content is structured in three tiers, inspired by Game of Thrones / HBO:

Episode: 3–4 chapters bundled together (~10,000–15,000 words). Each episode is a self-contained dramatic unit with its own internal arc, question, and resolution or cliffhanger. This is the unit of release.

Season: 6–10 episodes (~60,000–150,000 words). One complete movement of Vaelen’s arc. Season 1 = Movement One (the collapse of the performance).

The Full Arc: 3 seasons = the complete first story of Sorathel. Roughly 18–30 episodes total.

Release Cadence

One episode every 2–3 weeks. Season 1 at 8 episodes takes approximately 4–5 months. Between seasons: a 3–4 week break for feedback collection, outline adjustment, and lore drops to maintain engagement.

Constraints & Approach

Limited resources. Heavy AI leverage for writing, marketing content, and community materials. Prose-first pipeline (no artist dependency). Creative distribution and community-building to compensate for no marketing budget.

# II. Current Status — What’s Been Locked

Everything below has been developed and approved through collaborative sessions.

| Element | Details | Status |
| --- | --- | --- |
| World Bible v1 (14 sections) | Cosmology, Turnings, Realms, Creatures, Eldren, Ethura, Factions, Magic, Geography, Civilization, Glossary | DONE |
| Core Naming System | Sorathel, Amarwen, Mirathyn, Ohn, Ethura, Solcara, Carathiel + linguistic direction (Ember & Silk + River & Thorn) | DONE |
| Narrative Philosophy | Libertarian moral architecture: values shown through consequences, not preaching. Individual agency > institutional power. | DONE |
| Emotional Architecture | Mirathyn = dependency/addiction. Ethura = depression. Amarwen = codependency. Mapped to modern human experiences. | DONE |
| Protagonist Profile | Vaelen — name, appearance, core psychology (mask/performance/hollowness), why he hears Amarwen (resonance, not destiny) | DONE |
| Protagonist Wound | The Arrival That Was Empty — he achieved everything, felt nothing. Starts at center, successful and hollow. (Specific details still being refined) | 90% |
| Three-Movement Arc | M1: Successful life collapses. M2: The Void — factions, companions, hearing Amarwen. M3: The Choice — reaching Amarwen, offering evidence. | DONE |
| First Arc Ending | Not salvation. A pause. The question shifts from “hold on or let go” to “what is Sorathel when it stops performing?” | DONE |
| Civilization Design | Vethara (beauty of things ending), Hearthcircle system, cultural aesthetic fully developed | DONE |
| Faction Structure | 3 core (Athuri, Selvari, Veranthi) + 2 peripheral (Ohravel, Kaelthari). Kaelthari more prominent. | DONE |

# III. What’s Not Done — Open Items

| Item | Notes | Priority | Target Phase |
| --- | --- | --- | --- |
| Vaelen’s wound — final details | Arrival That Was Empty locked directionally. Needs specific scene-level details. | HIGH | Phase 1 |
| Inciting event | What disrupts Vaelen’s performance in a way he can’t manage? The specific world-event that pulls him out. | HIGH | Phase 1 |
| Companion ensemble | 3–4 characters who surround Vaelen. Names, backstories, arcs, faction connections. | HIGH | Phase 1 |
| Antagonist(s) | Who opposes Vaelen and why? Person, faction, structural force, or combination? | HIGH | Phase 1 |
| Season 1 episode outline | Beat-by-beat outline for all 6–10 episodes of Season 1. | HIGH | Phase 2 |
| Chapter-level breakdowns | Each episode’s 3–4 chapters mapped with scenes, POV, pacing. | MEDIUM | Phase 2 |
| Forbidden magic system | Full development of Ohn-drawn power. Who discovered it, costs, appearance. | MEDIUM | Phase 1 |
| Creature bonding mechanics | The full process of voluntary bonding for narrative purposes. | MEDIUM | Phase 3 |
| Pilot episode draft | Episode 1 written, revised, polished to publishable quality. | HIGH | Phase 3 |
| Platform setup | Royal Road / Tapas account, Discord server, newsletter. | MEDIUM | Phase 4 |
| Marketing content pipeline | Lore cards, character profiles, in-universe documents for social. | LOW | Phase 4 |
| Season 2–3 high-level outline | Movement Two and Three mapped at episode level (not chapter level yet). | LOW | Phase 5 |

# IV. Development Phases

Each phase has a clear entry condition (what must be true to start), deliverables, and exit condition (what must be true to move on).

## Phase 1 — Lock the Foundation

Timeline: 2–4 sessions (target: 1–2 weeks)

Entry condition: World Bible v1 complete, protagonist profile locked, three-movement arc locked.

Deliverables

1. Vaelen’s wound finalized with scene-level specificity.

2. The inciting event designed — the specific disruption that breaks his performance.

3. Companion ensemble built — 3–4 characters with names, backstories, arcs, faction ties.

4. Antagonist(s) designed — who or what opposes the protagonist.

5. Forbidden magic system fully developed.

6. World Bible v2 updated with all new material.

Exit condition: All major story elements locked. You could explain the entire Season 1 story to a stranger in 10 minutes and it would make sense and be compelling.

— ✦ —

## Phase 2 — Season 1 Architecture

Timeline: 2–3 sessions (target: 1–2 weeks)

Entry condition: Phase 1 complete. All characters, conflicts, and world elements locked.

Deliverables

1. Season 1 episode map — 6–10 episodes, each with a title, core question, and dramatic arc summary.

2. Chapter-level breakdowns for each episode — 3–4 chapters per episode, each with scenes, POV, pacing notes.

3. Opening and closing hooks for each episode defined.

4. Subplot tracking — companion arcs, faction tensions, Mirathyn thread, Ethura escalation mapped across the season.

5. Season 2–3 sketched at high level (episode-level only, not chapter-level).

Exit condition: You could read the episode outline document and know exactly what happens in every episode of Season 1, scene by scene.

— ✦ —

## Phase 3 — Pilot Episode

Timeline: 2–3 weeks

Entry condition: Phase 2 complete. Episode 1 outline locked at chapter and scene level.

Deliverables

1. Episode 1 first draft — full prose, 3–4 chapters, ~10,000–15,000 words.

2. Revision pass with creative director feedback — at least 2 rounds.

3. Final polish — publishable quality.

4. Episode 1 is the proof of concept. It must: introduce Vaelen mid-performance so the reader thinks he has it together; make the reader care about him within 2,000 words; hint at the world’s depth without explaining it; end with a hook that makes Episode 2 feel urgent.

Exit condition: You would be proud to share Episode 1 with anyone. It represents the quality bar for the entire series.

— ✦ —

## Phase 4 — Launch Infrastructure

Timeline: 1 week (can overlap with Phase 3)

Entry condition: Episode 1 in final draft. Confidence that you’re publishing.

Deliverables

1. Primary publishing platform account (Royal Road or Tapas) — profile set up, series page created, cover image, synopsis.

2. Discord server — basic channels: general, story-discussion, lore, feedback, announcements.

3. Newsletter — Substack or Buttondown free tier. Capture email signups from day one.

4. One social presence chosen (recommend Reddit — r/ProgressionFantasy, r/rational, relevant subs).

5. Pre-launch lore drop — one piece of marketing content (world map, faction overview, or character teaser) to seed interest before Episode 1 drops.

Exit condition: All platforms live. Ready to publish Episode 1 and send people somewhere.

— ✦ —

## Phase 5 — Season 1 Production

Timeline: ~4–5 months (6–10 episodes at one every 2–3 weeks)

Entry condition: Episode 1 published. Infrastructure live. Production pipeline tested.

Weekly Production Cycle (per episode)

Week 1, Mon–Wed: Draft episode (AI produces raw draft from outline, creative director shapes it).

Week 1, Thu–Fri: First revision pass.

Week 2, Mon–Wed: Second revision, polish, final read.

Week 2, Thu: Publish episode.

Week 2, Fri: Post-release — share on social, engage with comments, note feedback.

Between Episodes

Release one piece of supplementary content: lore card, character profile, in-universe document, faction deep-dive, creature profile, or short “interlude” scene.

Ongoing Community Work

Engage Discord daily (even briefly). Respond to Royal Road comments. Track which scenes/characters get the strongest reader reactions. Feed this data into future episode adjustments.

Exit condition: All Season 1 episodes published. Reader feedback collected and analyzed. Season 2 outline adjusted based on what you learned.

— ✦ —

## Phase 6 — Season Break

Timeline: 3–4 weeks

Entry condition: Season 1 complete.

Deliverables

1. Feedback analysis — what worked, what didn’t, what readers want more of.

2. Season 2 outline finalized at episode and chapter level.

3. Lore drops during the break to maintain engagement (3–4 pieces of content).

4. Community engagement — polls, Q&As, theory discussions. Let readers feel ownership.

5. Optional: compiled Season 1 as a downloadable ebook (free or paid).

6. Optional: Patreon/Ko-fi launch for early access to Season 2 episodes.

Exit condition: Season 2 ready to produce. Community engaged and waiting for more.

— ✦ —

## Phase 7 — Season 2 & Beyond

Timeline: Repeat Phases 5–6 for each season

Season 2 covers Movement Two (The Void — factions, companions, hearing Amarwen). Season 3 covers Movement Three (The Choice — reaching Amarwen, the pause). Same production pipeline, same cadence, but with the advantage of an established audience and lessons learned.

Upgrade Path (revenue-dependent)

After Season 1 or 2, if the audience is growing:

Tier 1: Commission character art and cover art. AI-assisted concept art for backgrounds.

Tier 2: Begin manhwa adaptation of the most popular episodes. Human artist for character work.

Tier 3: Compiled volumes (print-on-demand or traditional publishing pitch with proven audience numbers).

Tier 4: Game development begins with built-in fanbase.

# V. Master Timeline

Estimates assume 5–10 hours/week of creative director time. AI handles heavy production lifting.

| When | Phase | What | Status |
| --- | --- | --- | --- |
| Weeks 1–2 | Phase 1 | Lock foundation: wound, inciting event, companions, antagonist, forbidden magic | IN PROGRESS |
| Weeks 3–4 | Phase 2 | Season 1 episode map + chapter breakdowns | NOT STARTED |
| Weeks 5–7 | Phase 3 | Pilot episode: draft, revise, polish | NOT STARTED |
| Week 6–7 | Phase 4 | Launch infrastructure: Royal Road, Discord, newsletter, social | NOT STARTED |
| Weeks 8–28 | Phase 5 | Season 1 production: 6–10 episodes, one every 2–3 weeks | NOT STARTED |
| Weeks 29–32 | Phase 6 | Season break: feedback, Season 2 outline, lore drops | NOT STARTED |
| Weeks 33+ | Phase 7 | Season 2 production begins. Repeat cycle. | NOT STARTED |

Total time to Season 1 finale: approximately 7 months from today.

Total time to complete first arc (3 seasons): approximately 18–22 months.

# VI. Immediate Next Steps

These are the specific tasks for the next 1–2 sessions. This is where we pick up.

| # | Task | Details | Target |
| --- | --- | --- | --- |
| 1 | Finalize Vaelen’s wound at scene level | Refine the “Arrival That Was Empty” with concrete details: who was there, what he felt, the specific moment he knew | Session 1 |
| 2 | Design the inciting event | What disrupts Vaelen’s performed life? Must demand something authentic he can’t give. | Session 1 |
| 3 | Build companion ensemble | 3–4 characters: names, backstories, arcs, why they attach to Vaelen’s real self | Session 1–2 |
| 4 | Design antagonist(s) | Person, faction, force? What do they want and why does it conflict with Vaelen? | Session 2 |
| 5 | Develop forbidden magic | Ohn-drawn power: discovery, mechanics, costs, who uses it | Session 2 |
| 6 | Update World Bible to v2 | Consolidate all new material into the master document | Session 2–3 |
| 7 | Map Season 1 episodes | 6–10 episodes with titles, arcs, and chapter breakdowns | Session 3 |

— ✦ —

The single most important thing right now is finishing Phase 1. Everything else — platforms, marketing, monetization — is only valuable if the story lands. Let’s build the characters and write something that makes people feel.